{"text_format":"3","workbook":"xls","n_sheets":4,"sheets":["版权说明","产品Backlog","团队速率","发布燃尽图"],"not_rendered":{"charts":1,"external_links":2,"defined_names":2},"unopened":[{"sheet":"发布燃尽图","index":3,"reason":"not_a_worksheet"}],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"版权说明","index":0,"n_rows":10,"n_cols":3,"rows_kept":10,"flags":["formulas_cached_only"]}
{"$rows_empty":7}
[null,null,"本模板由Scrum中文网提供，欢迎推荐给任何在实践Scrum的朋友使用。"]
[]
[null,null,"Scrum中文网(ScrumCN.COM)版权所有"]

{"sheet":"产品Backlog","index":1,"n_rows":45,"n_cols":18,"rows_kept":45,"merged":[[0,0,2,1]],"flags":["formulas_cached_only"]}
["产品Backlog",null,"产品（项目）名称",{"$nulls":9},"Sprints"]
[null,null,"产品负责人",{"$nulls":6},"总的工作量",517,null,1,2,3,4,5,6]
[{"$nulls":12},517,436,350]
[{"$nulls":4},"totals",null,0]
["PBI_ID","优先级 ","Backlog类型","功能性/非功能性","用户故事（产品Backlog条目描述）","验收条件（满意条件）","复杂度","Sprint","初始工作量估计\n(用户故事点)","调整系数","调整后\n工作量估计\n(用户故事点)","状态"]
["PBI_01",100,"新需求","功能性","用户故事示例1",null,null,"Sprint1",5,1,5,"完成"]
["PBI_02",200,"缺陷","功能性","用户故事示例2",null,null,"Sprint1",3,1,3,"完成"]
["PBI_03",300,"新需求","功能性","用户故事示例3",null,null,"Sprint1",5,1,5,"完成"]
["PBI_04",400,"新需求","功能性","用户故事示例4",null,null,"Sprint1",10,1,10,"完成"]
["PBI_05",500,"新需求","功能性","用户故事示例5",null,null,"Sprint1",5,1,5,"完成"]
["PBI_06",600,"新需求","非功能性","用户故事示例6",null,null,"Sprint1",15,1,15,"完成"]
["PBI_07",700,"新需求","功能性","用户故事示例7",null,null,"Sprint1",10,1,10,"完成"]
["PBI_08",800,"新需求","功能性","用户故事示例8",null,null,"Sprint1",8,1,8,"完成"]
["PBI_09",900,"新需求","功能性","用户故事示例9",null,null,"Sprint1",15,1,15,"完成"]
["PBI_10",1000,"新需求","非功能性","用户故事示例10",null,null,"Sprint1",5,1,5,"完成"]
["PBI_11",1100,"新需求","功能性","用户故事示例11",null,null,"Sprint2",10,1,10,"完成"]
["PBI_12",1200,"新需求","功能性","用户故事示例12",null,null,"Sprint2",5,1,5,"完成"]
["PBI_13",1300,"新需求","功能性","用户故事示例13",null,null,"Sprint2",15,1,15,"完成"]
["PBI_14",1400,"缺陷","功能性","用户故事示例14",null,null,"Sprint2",10,1,10,"完成"]
["PBI_15",1500,"缺陷","功能性","用户故事示例15",null,null,"Sprint2",8,1,8,"完成"]
["PBI_16",1600,"新需求","功能性","用户故事示例16",null,null,"Sprint2",15,1,15,"完成"]
["PBI_17",1700,"新需求","功能性","用户故事示例17",null,null,"Sprint2",3,1,3,"完成"]
["PBI_18",1800,"新需求","功能性","用户故事示例18",null,null,"Sprint2",5,1,5,"完成"]
["PBI_19",1900,"新需求","功能性","用户故事示例19",null,null,"Sprint2",10,1,10,"完成"]
["PBI_20",2000,"新需求","功能性","用户故事示例20",null,null,"Sprint2",5,1,5,"完成"]
["PBI_21",2100,"新需求","功能性","用户故事示例21",null,null,"Sprint3",10,1,10,"未开始"]
["PBI_22",2200,"新需求","功能性","用户故事示例22",null,null,"Sprint3",15,1,15,"未开始"]
["PBI_23",2300,"新需求","功能性","用户故事示例23",null,null,"Sprint3",20,1,20,"未开始"]
["PBI_24",2400,"新需求","功能性","用户故事示例24",null,null,"Sprint3",20,1,20,"未开始"]
["PBI_25",2500,"新需求","功能性","用户故事示例25",null,null,"Sprint3",10,1,10,"未开始"]
["PBI_26",2600,"新需求","功能性","用户故事示例26",null,null,"Sprint3",10,1,10,"未开始"]
["PBI_27",2700,"新需求","功能性","用户故事示例27",null,null,"Sprint4",20,1,20,"未开始"]
["PBI_28",2800,"新需求","功能性","用户故事示例28",null,null,"Sprint4",20,1,20,"未开始"]
["PBI_29",2900,"新需求","功能性","用户故事示例29",null,null,"Sprint4",10,1,10,"未开始"]
["PBI_30",3000,"新需求","功能性","用户故事示例30",null,null,"Sprint4",10,1,10,"未开始"]
["PBI_31",3100,"新需求","功能性","用户故事示例31",null,null,"Sprint4",20,1,20,"未开始"]
["PBI_32",3200,"新需求","功能性","用户故事示例32",null,null,"Sprint5",20,1,20,"未开始"]
["PBI_33",3300,"新需求","功能性","用户故事示例33",null,null,"Sprint5",15,1,15,"未开始"]
["PBI_34",3400,"新需求","功能性","用户故事示例34",null,null,"Sprint5",25,1,25,"未开始"]
["PBI_35",3500,"新需求","功能性","用户故事示例35",null,null,"Sprint5",15,1,15,"未开始"]
["PBI_36",3600,"新需求","功能性","用户故事示例36",null,null,"Sprint5",20,1,20,"未开始"]
["PBI_37",3700,"新需求","功能性","用户故事示例37",null,null,"Sprint6",20,1,20,"未开始"]
["PBI_38",3800,"新需求","功能性","用户故事示例38",null,null,"Sprint6",15,1,15,"未开始"]
["PBI_39",3900,"新需求","功能性","用户故事示例39",null,null,"Sprint6",25,1,25,"未开始"]
["PBI_40",4000,"新需求","功能性","用户故事示例40",null,null,"Sprint6",30,1,30,"未开始"]

{"sheet":"团队速率","index":2,"n_rows":15,"n_cols":7,"rows_kept":15,"flags":["formulas_cached_only"]}
[]
[]
[]
[]
[]
[null,null,"团队1"]
[]
[null,null,"Sprint 1","Sprint 2","Sprint 3","Sprint 4","Sprint 5"]
[null,null,75,80,85,80,90]
[]
[]
[null,null,"团队2"]
[]
[null,null,"Sprint 1","Sprint 2","Sprint 3","Sprint 4","Sprint 5"]
[null,null,80,85,75,80,85]